Project Planning Phase

Product Backlog, Sprint Planning, Stories & Story Points

| Date | 08 March 2026 |
| --- | --- |
| Team ID | 699ee183888d59413178098c |
| Project Name | Quotes Recommendation Chatbot Using Rasa NLU |
| Maximum Marks | 8 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

| Sprint | Epic | USN | User Story / Task | Points | Priority | Team Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | DEFINE PROBLEM | USN-1 | As a team, we specify the business problem and document the core challenges faced by users seeking quote recommendations. | 2 | High | Aparna Anil |
| Sprint-1 | DEFINE PROBLEM | USN-2 | As a team, we define business requirements covering NLU support, multi-category quotes, web accessibility, and performance. | 2 | High | Aparna Anil |
| Sprint-1 | DEFINE PROBLEM | USN-3 | As a team, we conduct a literature survey on conversational AI, Rasa NLU, and emotional well-being chatbots. | 2 | High | Aparna Anil |
| Sprint-1 | DEFINE PROBLEM | USN-4 | As a team, we document the social and business impact of the chatbot on users and organizations. | 2 | Medium | Aparna Anil |
| Sprint-1 | Prerequisites | USN-5 | As a developer, I identify and document all prerequisites including software, libraries, and hardware requirements. | 2 | High | Kalyani Agarawal |
| Sprint-1 | Project Workflow | USN-6 | As a team, we define the end-to-end project workflow from user input to quote delivery. | 2 | High | Kalyani Agarawal |
| Sprint-2 | ENVIRONMENT SETUP | USN-7 | As a developer, I install Rasa and all required dependencies in a virtual environment. | 3 | High | Kalyani Agarawal |
| Sprint-2 | ENVIRONMENT SETUP | USN-8 | As a developer, I set up the Rasa project structure with all necessary configuration files. | 3 | High | Kalyani Agarawal |
| Sprint-3 | DATA COLLECTION & MODEL BUILDING | USN-9 | As a developer, I create the NLU training data (nlu.yml) with user queries for all quote categories. | 3 | High | Biswa Ranjan Mohanty |
| Sprint-3 | DATA COLLECTION & MODEL BUILDING | USN-10 | As a developer, I define bot responses and intents in domain.yml. | 3 | High | Biswa Ranjan Mohanty |
| Sprint-3 | DATA COLLECTION & MODEL BUILDING | USN-11 | As a developer, I define user-chatbot interaction flows using stories.yml. | 3 | High | Biswa Ranjan Mohanty |
| Sprint-3 | DATA COLLECTION & MODEL BUILDING | USN-12 | As a developer, I train the Rasa model using the configured pipeline and policies. | 3 | High | Biswa Ranjan Mohanty |
| Sprint-3 | DATA COLLECTION & MODEL BUILDING | USN-13 | As a developer, I store the trained model and document its reusability for future deployments. | 2 | Medium | Aparna Anil |
| Sprint-4 | TESTING & DEPLOYMENT | USN-14 | As a developer, I test the chatbot model using Rasa Shell to validate intent recognition. | 3 | High | Divyansh Chaudhary |
| Sprint-4 | TESTING & DEPLOYMENT | USN-15 | As a developer, I run automated tests using Rasa test stories to validate conversation flows. | 3 | High | Divyansh Chaudhary |
| Sprint-4 | TESTING & DEPLOYMENT | USN-16 | As a developer, I deploy the chatbot using a web interface connected to the Rasa REST API. | 3 | High | Divyansh Chaudhary |
| Sprint-4 | TESTING & DEPLOYMENT | USN-17 | As a developer, I validate the deployed chatbot for functionality, accuracy, and usability. | 3 | High | Divyansh Chaudhary |
| Sprint-4 | CONCLUSION | USN-18 | As a team, we capture screenshots of the working chatbot for documentation and submission. | 2 | Medium | Aparna Anil |
| Sprint-4 | CONCLUSION | USN-19 | As a team, we document future enhancements including mobile integration and multilingual support. | 2 | Low | Kalyani Agarawal |

Project Tracker, Velocity & Burndown Chart (4 Marks)

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 20 | 6 Days | 22 Feb 2026 | 27 Feb 2026 | 20 | 27 Feb 2026 |
| Sprint-2 | 20 | 6 Days | 28 Feb 2026 | 05 Mar 2026 | 20 | 05 Mar 2026 |
| Sprint-3 | 20 | 6 Days | 06 Mar 2026 | 11 Mar 2026 | 18 |  |
| Sprint-4 | 20 | 6 Days | 12 Mar 2026 | 17 Mar 2026 |  |  |

Velocity:

The team's velocity is 20 story points per sprint with a 6-day sprint duration.

Average Velocity (AV) = Story Points per Sprint / Sprint Duration = 20 / 6 = 3.33 story points per day

Burndown Chart:

A burndown chart is a graphical representation of work remaining versus time. For this project, the total story points across all 4 sprints = 80 points. At a velocity of 20 points per sprint, the team is expected to complete all work within the planned 4-sprint timeline.

| Sprint | Remaining Points (Ideal) | Remaining Points (Actual) | Status |
| --- | --- | --- | --- |
| Sprint-1 | 60 | 60 | On Track |  |  |  |
| Sprint-2 | 40 | 40 | On Track |  |  |  |
| Sprint-3 | 20 | 22 | Slightly Behind |  |  |  |
| Sprint-4 | 0 | - | In Progress |  |  |  |

References:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/burndown-charts

https://www.atlassian.com/agile/tutorials/sprints